## Sprint
|  |  |  | Week #1 (5 hrs / week) | [6 empty] | Week #2 (5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 10 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12
|  |  |  | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27
|  |  |  | 40 | 36 | 32 | 28 | 24 | 0 | 20 | 16 | 12 | 8 | 4 | 2 | Ideal Burndown
|  |  | 40 | 0 | 0.5 | 3.5 | 3.5 | 3.5 | 0 | 4 | 4 | 4 | 4 | 4 | 2 | Remaining Hrs (Total)
Project Set-up | Intial Project set-up in Gradle | Anushri | 2 | 2018-07-16: 1; 2018-07-17: 0.5; 2018-07-18: 0.5
Starbucks Rest API Implementation | Order Manage API - Research on modelling, interface definitions | Anushri | 2
| User Authentication API - Research on modelling, interface definitions | Saloni | 2 | bar: 2018-07-16 to 2018-07-27
| Add Card API - Research on modelling, interface definitions | Anu | 2 | bar: 2018-07-16 to 2018-07-27
| Payment API - Research on modelling, interface definitions | Hema | 2 | bar: 2018-07-16 to 2018-07-27
| Implementation of User Authentication API | Saloni
| Implementation of manage order contracts - models + interfaces | Anushri
| Implementation of manage order business logic | Anushri
| Implementation of REST Services for manage order | Anushri
| Integration of manage order with payment API | Anushri
| Implementing unit test cases for manage order | Anushri
| Implementation of Add Card API | Anu
| Implementation of Payment API | Hema
| Deploy initial project setup on EC2 and install necessary resources | Anushri | 1 | 2018-07-19: 0.5; 2018-07-20: 0.5
Cloud Deployment | Deploy API to AWS in an Auto Scaled EC2 Cluster with Load Balancer
| Deploy API to AWS as Docker Containers in Amazon EKS | Hema
Team:
Anushri Srinath Aithal | 5 hours / Week
Anu Sebastian | 5 hours / Week
Hemambujam Veeraraghavan | 5 hours / Week
Saloni Sharad Bhalerao | 5 hours / Week
Total Available Hours During Sprint: | 40